## Sheet1
TASK	Number	STATUS	START	END
Stage-1	1	In-Progress	17-5-31-2200
Stage-2	2	Contingent #1
Stage-3	3	Contingent #2
Stage-4	4	Contingent #3
Stage-5	5	Contingent #4
Stage-6	6	Contingent #5
Implement 8b RCA4	7	In-Progress
Preform Delay & Area analysis of 8b RCA4	8	Contingent #7
Implement 8b CSA	9	-
Preform Delay & Area analysis of 8b CSA	10	Contingent #9
Implement 8b Lynch-Swartzlander adder	11	-
Preform Delay & Area analysis of 8b Lynch-Swartzlander adder	12	Contingent #11